Template:  Milestone Table with Driver Tasks

What: Format for a milestone table that includes not only the completion dates for each critical milestone, but also provides a place to indicate the status of major driving tasks for each milestone.

Why:  Milestone tables are an excellent way to communicate overall project progress (or issues, if milestone dates are not being met).  To get the most accurate reading of the progress to each milestone, though, the team must understand what key activities must be completed for the milestone to be achieved.  This table provides a format for keeping those driving tasks highly visible and related to the milestones.

How:     This table is created during the planning of the project, and used throughout the project for tracking and communication.

- As you plan the project, identify key milestones the team should track.  Some will the actual “business milestones” driving the project schedule- for instance, needed delivery dates to particular customers or users; demonstration at a trade show; etc. Others will be key “internal” milestones that are critical points of progress – for instance, the point at which the project’s deliverables are in a form that can be reviewed or tested by users/customers.

- For each milestone that will be tracked, identify the key driving tasks/groups of tasks that must be done for the milestone to be achieved.  Add those to the table, along with a designated “responsible person”.

- Record the baseline scheduled date for each milestone.  This will come from your detailed planning and scheduling activities.

- Update the table prior to each team meeting.   Get “status information” on each driving task from each responsible person ahead of a team meeting.

- Determine from that status whether a milestone appears to be in jeopardy.  Include a revised date in the “projected completion date” column if necessary.

- Use the table in each team meeting, to quickly review status against milestones.  Bring an updated table to the team meeting.  Go down the milestone list, and have each person who is listed as responsible for a driving task quickly explain the status of that task, and whether they believe the milestone is thus on target, or threatened.  Discuss any changes the project manager has made to the “projected completion date” for that milestone, and why.

- Determine actions the team needs to take, if any, to get the milestone back on track.

- Determine whether the schedule baseline should change.   At some point, the team may decide that the schedule has to be re-baselined, in which case the “baseline” column would be updated to a new baseline level, and the new baseline dates recorded.   This should generally only be done if major issues have been encountered and significant replanning has to occur.   A baseline change should not be done “too easily”- that would undermine the value of identifying and tracking critical milestones.  If a re-baseline does become necessary, record the reason for the baseline change in a “Baseline History” section after the table itself.

Project X   Milestones Table   Page 1 of 4     Rev  ___

| Milestone | Rev 0 Baseline Date | Current Projected date | Driving Tasks | Responsible Person | Status/Comments |
| --- | --- | --- | --- | --- | --- |
| Core team formed | 29 Jan 04 | COMPLETE 29 Jan 04 | Completion of concept definition | M. Spears |  |
| Draft requirements document | 22 Feb 04 | COMPLETE 22 Feb 04 | Internal inputs, all functional groups | J. Lake | Each group to schedule whatever working sessions they need to have all their functional inputs together for the spec |
| Preliminary Scope Review | 15 Mar 04 | COMPLETE 17 Mar 04 | High level designs ready | M. Spears, S. Smith |  |
|  |  |  | Major tradeoffs submitted to VP | J. Lake | Want management reading on major tradeoffs prior to full team review |
| Initial Plan created | 5 Apr 04 | 12 Apr 04 | Scope decisions/ open issues from review | J. Lake | If open scope issues, initial plan will show both alternatives |
|  |  |  | Test strategy defined | M. Reed | Necessary to estimate full scope of project - covers internal and external testing |
|  |  |  | Vendor options | K. Cook | Outsource options for work – will impact budget |
|  |  |  | Functional group estimates | M. Spears | May be issue here – bandwidth of team members to spend on estimates to meet current deadline |

Continued next page

Project X   Milestones Table   Page 2 of 2    Rev  ___

| Milestone | Rev 0 Baseline Date | Current Projected date | Driving Tasks | Lead | Status/Comments |
| --- | --- | --- | --- | --- | --- |
| First system iteration ready for test | 15 May 04 | 29 May 04 | Feature 1 designed, prototyped | M. Spears |  |
|  |  |  | Feature 2 designed, prototyped | S. Smith | Uncertainty on this date until Vendor negotiations completed |
| Documentation plan drafted | 29 May 04 | 29 May 04 | Input from functional groups | D. Lane |  |
| System design review | 2 Jun 04 | 2 Jun 04 | First system test iteration complete | M. Spears |  |
|  |  |  | Documentation plan | D. Lane |  |
|  |  |  | Customer feedback from “early peek” at Feature 1 | J. Lake |  |

(insert more mid-project milestones here as appropriate)

| Start full system tests at customer | 22 Jun 04 | ?? 22 Apr 04 (depends on holding above date for first testing iteration) | Draft user documentation ready | D. Lane |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Customer training drafted | D. Lane |  |
|  |  |  | Special feature x ready | M. Spears |  |
|  |  |  | Internal testing completed | G. Gund |  |
|  |  |  | Customer signoff on test plan received | J. Lake |  |
|  |  |  | System updated with all changes | M. Spears |  |

(insert more later -project milestones here as appropriate)